## Sprint 4
Sprint 4 |  |  |  |  | Burnup Chart
User Story | Time | To Do | In Progress | Done | Iteration | Work Completed | Total Work | Burnup Line
4.1 | 20 |  |  | Plan integration of planned training with completed activities in terms of presentation to users - 2 hours Build database collection to house planned activities - 3 hours Build db and backend src files to interact with planned activities collection - 4 hours Build out plan training page inspired by existing calendar page - 5 hours Link up backend and frontend - 3 hours Debugging - 3 hours | 1 | 10 | 8 | 50
4.2 | 12 |  |  | Build accessor functions for planned training - 3 hours Build a frontend that displays totals for planned training statistics - 5 hours Combine planned training statistics component with plan training page and assure consistent look with previous activities page - 4 hours | 2 | 15 | 16 | 50
4.3 | 10 |  |  | Use accessor functions to fetch both completed and planned activities - 4 hours Build graphical display components for sport breakdown for planned and completed activities both separated and together - 3 hours Build UI for selecting graph to view and link with graph generation - 3 hours | 3 | 17 | 24 | 50
4.4 | 8 |  |  | Use accessor functions to fetch both completed and planned activities - 4 hours Build graphical display components for sport breakdown for planned and completed activities both separated and together - 3 hours Update UI for selecting graphs to view and link with graph generation - 1 hour | 4 | 38 | 33 | 50
[5 empty] | 5 | 50 | 41 | 50
[5 empty] | 6 | 62 | 50 | 50
Individual Work Log
[5 empty] | Name | Ethan | Fabrice | Daniel | Tung | Total
[5 empty] | 1 (until May 24) | 4 | 3 | 1 | 2 | 10
[5 empty] | 2 (until May 27) | 0 | 5 | 0 | 0 | 5
[5 empty] | 3 (until May 29) | 0 | 2 | 0 | 0 | 2
[5 empty] | 4 (until May 31) | 5 | 6 | 5 | 5 | 21
[5 empty] | 5 (until June 3) | 4 | 2 | 4 | 2 | 12
[5 empty] | 6 (until June 5) | 4 | 3 | 3 | 2 | 12

## Sprint 3
Sprint 3 |  |  |  |  | Burnup Chart
User Story | Time | To Do | In Progress | Done | Iteration | Work Completed | Total Work | Burnup Line
3.1 | 12 |  |  | Build front end page for displaying starred activities with total value summaries - 5 hours Write backend functions to calculate total values for activities - 4 hours Link backend with frontend - 1 hour Testing and revisions - 2 hours | 1 | 5 | 11 | 62
3.2 | 10 |  |  | Build front end page for general information summaries- 3 hours Write backend functions to fetch relevant data points for the user - 3 hours Link backend with frontend - 2 hour Testing and revisions - 2 hours | 2 | 20 | 22 | 62
3.3 | 10 |  |  | Adapt goal MUI cards for activities - 3 hours Link to MUI cards wherever activities are listed - 5 hours Enforce and assure consistency across frontend code for activity and goals cards MUI cards for manual activities | 3 | 30 | 33 | 62
3.4 | 15 |  |  | Identify key training volume metrics to visualize in graphs - 1 hours Build front end components for quality graphs showing general training volume - 4 hours Write backend functions to fetch and process training volume data - 3 hours Testing and revisions - 2 hours Write Matplotlib graphing code - 5 hours | 4 | 44 | 44 | 62
3.5 | 15 |  |  | Consider key metrics for sports-specific visualization in graphs - 1 hours Implement front end components for quality graphs curated for specific sports - 4 hours Testing and revisions - 2 hours Write Matplotlib graphing code - 5 hours Write backend functions to fetch and process sports-specific data - 2 hours | 5 | 52 | 55 | 62
| 62 |  |  |  | 6 | 64 | 62 | 62
Individual Work Log
[5 empty] | Name | Ethan | Fabrice | Daniel | Tung | Total
[5 empty] | 1 (until May 10) | 0 | 3 | 2 | 0 | 5
[5 empty] | 2 (until May 13) | 3 | 5 | 4 | 3 | 15
[5 empty] | 3 (until May 15) | 1 | 5 | 0 | 4 | 10
[5 empty] | 4 (until May 17) | 2 | 5 | 3 | 4 | 14
[5 empty] | 5 (until May 19) | 2 | 2 | 2 | 2 | 8
[5 empty] | 6 (until May 22) | 4 | 1 | 6 | 1 | 12

## Sprint 2
Sprint 2 |  |  |  |  | Burnup Chart
User Story | Time | To Do | In Progress | Done | Iteration | Work Completed | Total Work | Burnup Line
2.1 | 14 |  |  | Write API and database functions to get sports requested by users - 4 hours Build front end page for filters with a form element - 5 hours Link backend with frontend - 1 hour Testing and revisions - 4 hours | 1 | 14 | 9 | 53
2.2 | 11 |  |  | Build front end page with form element for adding new workout - 5 hours Write database functions to store new workout - 2 hours Testing and revisions - 4 hours | 2 | 25 | 18 | 53
2.3 | 3 |  |  | Add front end form to add more detailed workout data - 2 hours Build backend mechanism to store more detailed information in the database - 1 hour | 3 | 38 | 27 | 53
2.4 | 11 |  |  | Write API and database functions to store new goal - 2 hours Testing and revisions - 2 hours Build front end page with form element for adding new goal - 5 hours | 4 | 45 | 36 | 53
2.5 | 3 |  |  | Update goal adding element to include sport to goal matching - 2 hours Update goal storage in database to include new metadata - 1 hour | 5 | 56 | 45 | 53
2.6 | 11 |  |  | Implement race goal specific features from 2.41 - 3 hours Write API and database functions to store new goal - 2 hours Testing and revisions - 2 hours Revise front end page to allow setting race goal in addition to 2.3 - 2 hours Consider race goal features apart from regular goal features - 2 hours | 6 | 68 | 53 | 53
| 53 |  |  |  | Individual Work Log
[5 empty] | Name | Ethan | Fabrice | Daniel | Tung | Total
[5 empty] | 1 (until April 26) | 3 | 3 | 6 | 2 | 14
[5 empty] | 2 (until April 29) | 3 | 3 | 2 | 3 | 11
[5 empty] | 3 (until May 1) | 3 | 3 | 4 | 3 | 13
[5 empty] | 4 (until May 3) | 1 | 4 | 1 | 1 | 7
[5 empty] | 5 (until May 7) | 1 | 3 | 4 | 3 | 11
[5 empty] | 6 (until May 8) | 3 | 3 | 3 | 3 | 12

## Sprint 1
Sprint 1 |  |  |  |  | Burnup Chart
User Story | Time | To Do | In Progress | Done | Iteration | Work Completed | Total Work | Burnup Line
1.1 | 10 |  |  | Build sign up form for login page - 2 Link up sign up form with home page and database - 3 Storage of usernames/passwords/accounts - 5 | 1 | 5 | 10 | 61
1.2 | 10 |  |  | Build sign in form for login page - 2 Link up sign in form with home page and database - 3 Verification of usernames/passwords and issuing of authentication token - 5 | 2 | 13 | 20 | 61
1.3 | 8 |  |  | Plan page architecture -2 Make preliminary front end for home page and its components - 4 Link up home to future data, planning, and settings pages via button components and backend server - 2 | 3 | 24 | 28 | 61
1.4 | 8 |  |  | Plan settings page architecture -2 Make preliminary front end for settings page and its components - 4 Build list with starring of favorite sports | 4 | 27 | 36 | 61
1.5 | 14 |  |  | Learn about Strava API - 4 Integrate Strava login to authenticate TCC to scrape from Strava API - 4 Implement scraper to fetch Strava activities from user’s account - 4 | 5 | 36 | 50 | 61
1.6 | 11 |  |  | Build frontend layout pages that will host data - 3 Link pages up to home - 3 | 6 | 42 | 61 | 61
Unfinished work at the end of this sprint was completed during the first week of sprint 2. All complete as of Wednesday 5/3